## Sheet1
Date | Task | Duration Hrs | Start | End
2018-07-09 | Completing Requesting Laptop | 0.75
2018-08-09 | Completing Requesting Laptop | 1
2018-09-09 | Completing Requesting Laptop | 2
13/9/2018 | Completing Requesting Laptop | 2 | 4:30 | 6:30
14/9/2018 | Completing Requesting Laptop | 3 | 3:40 | 6:30
14/9/2018 | Completing Requesting Laptop | 0.5 | 10:00 | 10:30
16/9/2018 | Completing Approve Laptop Screen | 1 | 14:40 | 15:40 |  | 8106930
17/9/2018 | Completing Approve Laptop Screen | 0.25 | 13:00 | 13:15 |  | 75000
22/9/2018 | Testing in Sony Vaio Machine, introducing phoneext in detail table here | 4.5 | 16:00 | 20:30 |  | 8181930
23/9/2018 | Back end structure refined ie status introduced and worked on completing approve laptop screen | 1.5 | 6:15 | 7:45
23/9/2018 | Completing Approve Laptop Screen | 1 | 10:30 | 11:30
23/9/2018 | Completing Approve Laptop Screen | 1 | 18:15 | 19:14
24/9/2018 | testing request Laptop Screen | 0.25 | 6:00 | 6:15
25/9/2018 | Auto refreshing dashboad after successful laptop request | 1.25 | 4:00 | 5:15
26/9/2018 | Request Laptop should be enabled for all. But Approve Laptop button should be clicable only of the logged in user is an approver. Similarly Issue laptop and collect laptop should be clicable only for store keeper | 0.5 | 12:45 | 13:15
27/9/2018 | Completing Approve Laptop Screen | 1.25 | 4:45 | 6:00 | Ground work done
2018-08-10 | Mockups using balsmiq | 1:00 | 3:30 | 4:30
2018-08-10 | Packaging and sending to Prabs | 0.5 | 4:30 | 5:00
23/10/2018 | Continue working on approve laptop screen | 1.5 | 12:00 | 13:30
24/10/2018 | Continue working on approve laptop screen | 0.5 | 7:30 | 8:00
24/10/2018 | Continue working on approve laptop screen | 0.5 | 13:00 | 13:30
25/10/2018 | Continue working on approve laptop screen, ie debugging recording of approval | 2 | 7:00 | 9:00
26/10/2018 | Continue working on approve laptop screen, ie reject portion | 1 | 8:30 | 9:30
26/10/2018 | Continue working on approve laptop screen, ie reject portion | 0.25 | 10:00 | 10:15
29/10/2018 | Continue building this app..Issuelaptop | 2.25 | 10:45 | 13:00
30/10/2018 | Continue building this app..Issuelaptop ie recording laptops that are being issued in the database | 2:20 | 12:30 | 14:50 | For some reason, I could not figure out why the ISSUE button on the issue laptop modal was not working